## Items
ID | Tier | Category | Item | Specification | Qty | Ref. price | Cur. | Unit, USD | Ext., USD | Unit, KWD | Ext., KWD | Status | Price basis | Reference vendor | Reference URL | Checked | Checked via | Need by | For | Notes
A01 | A | Measurement and safety | Precision bench scale | 3 kg capacity, 0.1 g resolution, tare. Weighs bodies, ballast and containers to 0.01 oz (0.28 g). | 2 | 15 | USD | 15 | 30 | 4.6624 | 9.3249 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01, TC-02, TC-04 | Example model: Duratool D03412 (3 kg × 0.1 g).
A02 | A | Measurement and safety | Digital hanging scale | 50 kg × 10 g with hold function. Tension check; weighing payload bundles and airframes. | 1 | 15 | USD | 15 | 15 | 4.6624 | 4.6624 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01, TC-04
A03 | A | Measurement and safety | Vane anemometer | Handheld, 0.3–30 m/s, reads m/s and ft/min. | 1 | 26.99 | USD | 26.99 | 26.99 | 8.3893 | 8.3893 | Buy now | Listing | HoldPeak HP-866B (eBay) | https://www.ebay.ca/p/10014711598 | 2026-10-09 | Search result | 2026-10-11 | TC-01 | Upper limit 30 m/s (98 ft/s).
A04 | A | Measurement and safety | Digital caliper | 150 mm, 0.01 mm. Foam thickness and permanent set; simulator size match (±1/8 in). Skip if the lab has one. | 1 | 20 | USD | 20 | 20 | 6.2166 | 6.2166 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-02, §3.1.3
A05 | A | Measurement and safety | Safety glasses | Impact-rated (ANSI Z87.1 or EN 166). | 6 | 4 | USD | 4 | 24 | 1.2433 | 7.4599 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01, TC-02
A06 | A | Measurement and safety | Earmuffs | Passive hearing protection for blower runs. | 3 | 12 | USD | 12 | 36 | 3.7299 | 11.1898 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01
A07 | A | TC-01 blower rig | Leaf blower | Highest air volume available locally; target ≥ 15 m³/min (530 cfm). 230 V / 50 Hz or cordless; variable speed preferred. | 1 | 359 | USD | 359 | 359 | 111.5876 | 111.5876 | Buy now | Listing | EGO LB7654, 765 cfm, 56 V kit (Ace Hardware) | https://www.acehardware.com/departments/lawn-and-garden/outdoor-power-equipment/leaf-blowers/7026058 | 2026-10-09 | Search result | 2026-10-11 | TC-01 | US reference model. Buy the local equivalent and check its air-volume rating.
A08 | A | TC-01 blower rig | Duct and adapters | Rigid round duct, 100 mm and 150 mm × 1 m; reducer to the blower nozzle; aluminium tape; clamps. | 1 | 40 | USD | 40 | 40 | 12.4332 | 12.4332 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01
A09 | A | TC-01 blower rig | Drinking straws | Plain straight straws, about 6–8 mm × 200 mm, for the flow straightener. | 1 | 10 | USD | 10 | 10 | 3.1083 | 3.1083 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01 | About 500 straws.
A10 | A | TC-01 blower rig | Ball-bearing swivels | Fishing ball-bearing swivels, ≥ 50 lb rated. | 10 | 1.2 | USD | 1.2 | 12 | 0.373 | 3.7299 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01 | A swivel lets any roll tendency show as rotation.
A11 | A | TC-01 blower rig | Braided PE line | 50–80 lb braided PE (Dyneema-type) fishing line, ≥ 150 yd. | 1 | 20 | USD | 20 | 20 | 6.2166 | 6.2166 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01, TC-02, tow-line candidate
A12 | A | TC-01 blower rig | Ballast assortment | Steel nuts and washers M5–M10 and lead-free sinkers, about 1 kg. | 1 | 15 | USD | 15 | 15 | 4.6624 | 4.6624 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01, TC-02 | Ballast must be internal to the sensor (§3.1.1).
A13 | A | TC-02 drop test | Foam sheet assortment | At least 4 types: EPE (2 densities), EPS (2 densities), XPS, open-cell PU, EVA; 10, 20, 25 and 50 mm; about 0.5 m² per type and thickness. | 1 | 120 | USD | 120 | 120 | 37.2995 | 37.2995 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-02, Script 5 | Ask each supplier for density and the compressive stress–strain curve (crush stress, densification strain).
A14 | A | TC-02 drop test | Plywood and MDF sheets | 3 mm and 6 mm, laser-cutter bed size. | 6 | 8 | USD | 8 | 48 | 2.4866 | 14.9198 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-02 containers and fixture
A15 | A | TC-02 drop test | Brass rod | 1/4 in (6.35 mm) brass, 300 mm long, for the quick-release pin replica. 6 mm metric is acceptable for testing. | 2 | 6 | USD | 6 | 12 | 1.865 | 3.7299 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-02 | The contest pin is 1/4 in brass (§3.1.3).
A16 | A | TC-02 drop test | Welded steel rings | Welded (not split) stainless rings, wire diameter ≤ 3.0 mm, inside diameter ≥ 13 mm. | 10 | 1 | USD | 1 | 10 | 0.3108 | 3.1083 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-02, TC-04 | Rule: ID ≥ 1/2 in (12.7 mm), cross-section ≤ 1/8 in (3.18 mm) (§3.1.3).
A17 | A | TC-02 drop test | Rigging hardware assortment | Mini stainless snap hooks, quick links, ball-lock quick-release pins, crimp sleeves. | 1 | 30 | USD | 30 | 30 | 9.3249 | 9.3249 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-02, TC-04, SR-10
A18 | A | TC-02 drop test | High-g accelerometer (optional) | Adafruit H3LIS331 ±400 g breakout (product 4627), logged by a Pico (A24). | 1 | 24.95 | USD | 24.95 | 24.95 | 7.7552 | 7.7552 | Buy now | Listing | Adafruit | https://www.adafruit.com/product/4627 | 2026-10-09 | Vendor page | 2026-10-14 | TC-02 peak g | Optional. Without it, TC-02 still runs on damage checks and foam set.
A19 | A | TC-03 lights | Colour LED stars | Cree XP-E2 single-emitter 20 mm star: red, red-orange, amber (1000 mA max). | 6 | 5.71 | USD | 5.71 | 34.26 | 1.7748 | 10.649 | Buy now | Listing | LEDSupply (regular price; 0 in stock on 9 Oct) | https://www.ledsupply.com/leds/cree-xlamp-xp-e2-color-high-power-led-star | 2026-10-09 | Search result | 2026-10-14 | TC-03
A20 | A | TC-03 lights | White LED stars | Cree XP-E2 or XP-G white, 20 mm star. | 4 | 6 | USD | 6 | 24 | 1.865 | 7.4599 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03
A21 | A | TC-03 lights | LED optics | 20 mm star optics, narrow (about 15°) and medium (about 30°). | 8 | 2 | USD | 2 | 16 | 0.6217 | 4.9733 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03
A22 | A | TC-03 lights | Constant-current LED drivers | 350–700 mA buck modules with a PWM dimming input. | 6 | 3 | USD | 3 | 18 | 0.9325 | 5.5949 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03
A23 | A | TC-03 lights | 5 mm LEDs and LED strip | Ultra-bright 5 mm assortment (white, red, amber, green); 5 V SMD strip, 1 m each of white and red. | 1 | 20 | USD | 20 | 20 | 6.2166 | 6.2166 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03
A24 | A | EE bench | Microcontroller boards | Raspberry Pi Pico (RP2040): TC-03 flash-pattern driver, test-box prototype, A18 logger. | 4 | 4 | USD | 4 | 16 | 1.2433 | 4.9733 | Buy now | Listing | Raspberry Pi (list price) | https://www.raspberrypi.com/products/raspberry-pi-pico/ | 2026-10-09 | Vendor page | 2026-10-14 | TC-03, EE lane
A25 | A | EE bench | 1S LiPo packs, labelled | COTS 1S LiPo, 300–1000 mAh; the label shows chemistry, capacity, voltage and C-rating. | 4 | 8 | USD | 8 | 32 | 2.4866 | 9.9465 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03, sensor battery | The sensor battery must meet §3.2.3 (§3.1.1).
A26 | A | EE bench | 1S LiPo charger | USB charger for the A25 packs. | 1 | 12 | USD | 12 | 12 | 3.7299 | 3.7299 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03
A27 | A | EE bench | Inline current meter | USB / DC power meter, 0–5 A, 3–30 V. | 1 | 15 | USD | 15 | 15 | 4.6624 | 4.6624 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03
A28 | A | EE bench | Electronics consumables | Logic-level MOSFETs, resistor kit, perfboard, 26–30 AWG silicone wire, heat-shrink, breadboard, jumpers. | 1 | 35 | USD | 35 | 35 | 10.879 | 10.879 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-03, EE lane
A29 | A | Fabrication and mock-ups | PLA filament | 1.75 mm, 1 kg. | 3 | 23 | USD | 23 | 69 | 7.1491 | 21.4472 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01 bodies, TC-02 dummies, rig adapters | Bambu Lab PLA Basic seen at USD 19.99–22.99 in regional stores (search, 9 Oct).
A30 | A | Fabrication and mock-ups | PETG filament | 1.75 mm, 1 kg. | 2 | 23 | USD | 23 | 46 | 7.1491 | 14.2981 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | Containers, fixtures
A31 | A | Fabrication and mock-ups | TPU 95A filament | 1.75 mm, 1 kg. | 1 | 40 | USD | 40 | 40 | 12.4332 | 12.4332 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | Bumpers, liner trials
A32 | A | Fabrication and mock-ups | Hatch-latch candidates | Spring latches, R-clips and cotter pins, toggle latches, screw latches. | 1 | 25 | USD | 25 | 25 | 7.7707 | 7.7707 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-14 | TC-04, SR-04, SR-12 | Magnets are not an acceptable latching method (§4.2.1).
A33 | A | Fabrication and mock-ups | Mock-up materials | Cardboard sheets, hot-glue sticks, tape, paint markers (TOP / O / E markings, roll stripes). | 1 | 25 | USD | 25 | 25 | 7.7707 | 7.7707 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-10-11 | TC-01, TC-04
B01 | B | Radio (ExpressLRS) | ELRS transmitter | RadioMaster Boxer, internal ELRS 2.4 GHz, FCC version, EdgeTX. Skip if the pilot already owns a radio with internal ELRS 2.4 GHz. | 1 | 153.99 | USD | 153.99 | 153.99 | 47.8646 | 47.8646 | Buy now | Listing | RadioMaster | https://radiomasterrc.com/products/boxer-radio-controller-m2 | 2026-10-09 | Vendor page | 2026-11-01 | §3.2.1, §4.2.5 | Transmitter cells are not included (B02).
B02 | B | Radio (ExpressLRS) | Transmitter cells | 2 × 18650 Li-ion cells and a charger, for B01. | 1 | 20 | USD | 20 | 20 | 6.2166 | 6.2166 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | B01
B03 | B | Radio (ExpressLRS) | ELRS PWM receiver, 8 ch | RadioMaster ER8: 8 PWM outputs, 4.5–8.4 V, ELRS 3.3.0, FCC firmware. PWM output only: no CRSF-only receivers, which need a flight controller. | 3 | 34.99 | USD | 34.99 | 104.97 | 10.8759 | 32.6277 | Buy now | Listing | RadioMaster | https://radiomasterrc.com/products/er8-2-4ghz-elrs-pwm-receiver | 2026-10-09 | Vendor page | 2026-11-01 | §3.2.1, §4.2.1, §4.2.5 | One per airframe plus a spare. Fail-safe positions must be set in the receiver WebUI (default is centred).
B04 | B | Radio (ExpressLRS) | ELRS PWM receiver, 6 ch | RadioMaster ER6: bench receiver for sensor and reel development, or the observer's payload link (§3.1). | 1 | 24.99 | USD | 24.99 | 24.99 | 7.7676 | 7.7676 | Buy now | Listing | RadioMaster | https://radiomasterrc.com/products/er6-2-4ghz-elrs-pwm-receiver | 2026-10-09 | Vendor page | 2026-11-01 | EE lane, §3.1
B05 | B | Radio (ExpressLRS) | Receiver and servo battery | 2S LiFe 6.6 V (7.2 V full), about 1450 mAh, COTS with label. | 3 | 34.99 | USD | 34.99 | 104.97 | 10.8759 | 32.6277 | Buy now | Listing | Spektrum SPMB1450LFRX (Gator RC; out of stock on 9 Oct) | https://www.gator-rc.com/products/spektrum-1450-receiver-battery | 2026-10-09 | Vendor page | 2026-11-01 | §3.2.3 | A separate receiver battery is mandatory. 7.2 V full charge needs HV servos (B19).
B06 | B | Radio (ExpressLRS) | External receiver switch | Heavy-duty switch harness, mounted outside the airplane. An arming plug does not count as this switch. | 3 | 15 | USD | 15 | 45 | 4.6624 | 13.9873 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | §3.2.1
B07 | B | Propulsion and power | Motor candidates | Brushless outrunner; class set by Scripts 3–4 at the 13 Oct gate. Reference: T-Motor AT4130 long shaft (230/300/450 KV, 6–12S). | 3 | 119.9 | USD | 119.9 | 359.7 | 37.2684 | 111.8052 | Budget hold | Listing | T-Motor | https://shop.tmotor.com/products/at4130-long-shaft | 2026-10-09 | Vendor page | 2026-11-30 | §3.2.1, Scripts 3–4 | Unmodified commercial motor (§3.2.1).
B08 | B | Propulsion and power | ESC candidates | 80–100 A, matched to B07; BEC disabled. Reference: Castle Phoenix Edge Lite 100 (2–8S, 100 A). | 3 | 149.95 | USD | 149.95 | 449.85 | 46.6088 | 139.8264 | Budget hold | Listing | Gator RC | https://www.gator-rc.com/products/castle-creations-phoenix-edge-lite-100-esc-with-built-in-5-amp-bec | 2026-10-09 | Vendor page | 2026-11-30 | §3.2.3, FAQ A.3
B09 | B | Propulsion and power | Propellers and spares | APC Electric (E) series; diameter and pitch from Script 3. Reference: APC 15×10E. | 16 | 7.65 | USD | 7.65 | 122.4 | 2.3778 | 38.0455 | Budget hold | Listing | Gator RC | https://www.gator-rc.com/products/15x10e-propeller-electric-apc | 2026-10-09 | Search result | 2026-11-30 | §3.2.1 | Commercial propellers only; tips may be clipped (§3.2.1).
B10 | B | Propulsion and power | Propulsion LiPo packs | ≤ 100 Wh per pack and in total on the airplane. Reference: Tattu R-Line 6S 4500 mAh 95C, 99.9 Wh, XT90-S, 10 AWG leads. | 4 | 147 | USD | 147 | 588 | 45.6919 | 182.7675 | Budget hold | Listing | NextFPV (regular price; sale USD 128; backordered) | https://www.nextfpv.com/products/tattu-r-line-4500mah-95c-6s1p-lipo-battery-pack-with-xt90s-plug-for-uav | 2026-10-09 | Vendor page | 2026-11-30 | §3.2.3, §4.2.3 | Label must show chemistry, capacity, voltage and C-rating. Keep the original packaging (§4.2.3). Lithium packs ship as dangerous goods: buy locally if possible.
B11 | B | Propulsion and power | LiPo charging sacks | Commercial, unaltered, manufacturer-labelled; sized for the packs. Every battery (propulsion, receiver, sensor) is stored and charged in one. | 6 | 11.98 | USD | 11.98 | 71.88 | 3.7237 | 22.3424 | Buy now | Listing | Racers Edge (HobbyEtc) | https://store.hobbyetc.com/parts/view/132874 | 2026-10-09 | Search result | 2026-11-01 | §3.2.3
B12 | B | Propulsion and power | Balance charger | AC/DC, 1–6S LiPo and LiFe. Reference: ToolkitRC M7AC (retailers disagree on its power rating; check). Skip if the lab has one. | 1 | 96.99 | USD | 96.99 | 96.99 | 30.1473 | 30.1473 | Buy now | Listing | Pyrodrone | https://pyrodrone.com/collections/chargers-1/brand_toolkitrc | 2026-10-09 | Search result | 2026-11-01 | Battery care
B13 | B | Propulsion and power | MAXI blade fuses | Assortment: 40, 50, 60 and 80 A (Littelfuse MAXI 299 series) and 100 A (Littelfuse 0MAX100, purple). | 15 | 3 | USD | 3 | 45 | 0.9325 | 13.9873 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | §3.2.3.1, §3.2.3.2 | Fuse rating ≤ the pack's maximum continuous current, capped at 100 A.
B14 | B | Propulsion and power | Inline MAXI fuse holders | Rated at least as high as the fuse; for 10–12 AWG. Reference: GEP waterproof MAXI kit (up to 100 A, 12–10 AWG terminals, fuse not included). | 6 | 16.95 | USD | 16.95 | 101.7 | 5.2686 | 31.6113 | Buy now | Listing | CE Auto Electric Supply | https://ceautoelectricsupply.com/product/gep-waterproof-maxi-fuse-holder-kit/ | 2026-10-09 | Search result | 2026-11-01 | §3.2.3.1 | One fuse harness per propulsion pack.
B15 | B | Propulsion and power | Arming-plug connectors | XT90-S anti-spark pairs (or the packs' connector) and XT90E-M panel mounts. | 10 | 2.5 | USD | 2.5 | 25 | 0.7771 | 7.7707 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | §3.2.2 | Arming-plug wire must be the same gauge as the pack leads or heavier (10 AWG on the reference pack).
B16 | B | Propulsion and power | Silicone wire | 10 AWG and 12 AWG, red and black, 3 m of each. | 1 | 30 | USD | 30 | 30 | 9.3249 | 9.3249 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | §3.2.2
B17 | B | Propulsion and power | Watt meter | ToolkitRC WM150, 1–50 V, 150 A. | 1 | 51.99 | USD | 51.99 | 51.99 | 16.16 | 16.16 | Buy now | Listing | Pyrodrone | https://pyrodrone.com/products/toolkitrc-wm150-advanced-watt-power-meter | 2026-10-09 | Search result | 2026-11-01 | Thrust and energy tests
B18 | B | Propulsion and power | Thrust-stand parts | Load cell (≥ 5 kg), HX711 amplifier, frame stock. | 1 | 40 | USD | 40 | 40 | 12.4332 | 12.4332 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | Thrust test (proposal Table 10)
B19 | B | Airframe and hardware | HV digital servos | 6.0–8.4 V, metal gear; size and torque from sizing. | 16 | 45 | USD | 45 | 720 | 13.9873 | 223.7969 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2026-11-30 | §3.2.1 | HV rating needed for the 2S LiFe receiver pack (7.2 V full).
B20 | B | Airframe and hardware | Linkage hardware | Clevises with locking sleeves, commercial control horns, pushrods. | 1 | 40 | USD | 40 | 40 | 12.4332 | 12.4332 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | §3.2.1, §4.2.1 | Clevises need a mechanical lock. Horns go on per the manufacturer's instructions, never glued to film alone.
B21 | B | Airframe and hardware | Fasteners and threadlocker | Nylon-insert lock nuts, M2–M5 screws, washers, heat-set inserts, Loctite 243. | 1 | 60 | USD | 60 | 60 | 18.6497 | 18.6497 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | §3.2.1, §4.2.1 | Every permanent fastener needs a secondary retention method.
B22 | B | Airframe and hardware | Carbon-fibre tubes | Roll-wrapped; OD and wall from sizing (spar, tail boom). Reference: Rock West 45002, 3k twill, 0.983 × 1.055 × 72 in. | 4 | 99.99 | USD | 99.99 | 399.96 | 31.0798 | 124.3192 | Budget hold | Listing | Rock West Composites | https://www.rockwestcomposites.com/roll-wrapped-carbon-fiber-tubes | 2026-10-09 | Vendor page | 2026-11-30 | Sizing
B23 | B | Airframe and hardware | Balsa and aircraft plywood | Balsa sheet 1.5–6 mm; birch aircraft ply 1.5 and 3 mm. | 1 | 150 | USD | 150 | 150 | 46.6244 | 46.6244 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2026-11-30 | Sizing
B24 | B | Airframe and hardware | Foam boards | XPS or EPS, 50 mm, for hot-wire wing cores. | 6 | 15 | USD | 15 | 90 | 4.6624 | 27.9746 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2026-11-30 | Sizing
B25 | B | Airframe and hardware | Covering | Heat-shrink covering film or laminating film (the team has no composites capability). | 4 | 30 | USD | 30 | 120 | 9.3249 | 37.2995 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2026-11-30 | Manufacturing plan
B26 | B | Airframe and hardware | Landing gear and wheels | Set by the gear trade (tricycle or taildragger). | 2 | 60 | USD | 60 | 120 | 18.6497 | 37.2995 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2026-11-30 | Configuration trade
B27 | B | Airframe and hardware | Adhesives and shop consumables | CA (thin, medium, thick) and accelerator, 5- and 30-minute epoxy, hot glue, sandpaper, blades, zip ties, hook-and-loop, heat-shrink. | 1 | 150 | USD | 150 | 150 | 46.6244 | 46.6244 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | Build | The 2026 judges flagged missing consumables in the budget.
B28 | B | Sensor, D&R and test box | Slip rings | Capsule slip ring, 22 mm flange, 6 wires, 2 A, up to 300 rpm (Adafruit 736). | 3 | 14.95 | USD | 14.95 | 44.85 | 4.6469 | 13.9407 | Buy now | Listing | Adafruit | https://www.adafruit.com/product/736 | 2026-10-09 | Vendor page | 2026-11-01 | SR-06, SR-07
B29 | B | Sensor, D&R and test box | Reel actuator candidates | Multi-turn sail-winch servo or DC gearmotor with encoder; torque and turns from Script 5. | 3 | 45 | USD | 45 | 135 | 13.9873 | 41.9619 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2026-11-30 | SR-06, Script 5
B30 | B | Sensor, D&R and test box | Tow-line conductor | 2-conductor 28–30 AWG PTFE or silicone wire, 10 m. Strength member: the PE braid (A11). | 2 | 12 | USD | 12 | 24 | 3.7299 | 7.4599 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | SR-06, SR-07 | The tow line carries both the mechanical and the electrical connection (§3.1.1).
B31 | B | Sensor, D&R and test box | Locking micro connectors | JST-GH 2–4 pin with pre-crimped leads, for the tow-line electrical interface. | 1 | 20 | USD | 20 | 20 | 6.2166 | 6.2166 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | SR-07
B32 | B | Sensor, D&R and test box | Sensor light-controller MCU | Seeed XIAO RP2040 (21 × 17.5 mm). | 4 | 3.9 | GBP | 5.1593 | 20.6372 | 1.6037 | 6.4147 | Buy now | Listing | The Pi Hut (incl. VAT) | https://thepihut.com/collections/all/products/seeed-xiao-rp2040 | 2026-10-09 | Search result | 2026-11-01 | SR-07, §3.1.1 | Describe it only as payload light control.
B33 | B | Sensor, D&R and test box | Sensor test-box parts | 3-position switch, mating tow-line connector, printed enclosure, battery holder. Generates the same 1000 / 1500 / 2000 µs PWM as the receiver channel. | 2 | 20 | USD | 20 | 40 | 6.2166 | 12.4332 | Buy now | Estimate |  |  | 2026-10-09 |  | 2026-11-01 | §3.1.1, §3.3.4, §4.1 | Mandatory at tech inspection and in the Ground Mission.
B34 | B | Sensor, D&R and test box | Final sensor LEDs and batteries | Chosen from the TC-03 results. | 1 | 40 | USD | 40 | 40 | 12.4332 | 12.4332 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2026-11-30 | TC-03
B35 | B | Logistics | Shipping crate materials | Plywood, foam and hardware for a travel crate. | 1 | 150 | USD | 150 | 150 | 46.6244 | 46.6244 | Budget hold | Estimate |  |  | 2026-10-09 |  | 2027-03-01 | Travel | The 2026 judges flagged missing crating in the budget.
[8 empty] | Tier A, local purchase | 1280.2 |  | 397.9233
[8 empty] | Tier B, buy now | 1315.9672 |  | 409.0408
[8 empty] | Tier B, budget holds | 3444.91 |  | 1070.7779
[8 empty] | Total | 6041.0772 |  | 1877.742
[8 empty] | Share backed by a listing | 52.28%

## Read me
PR-01 Initial purchase request: test supplies and long-lead hardware
AIAA Design/Build/Fly 2026–27 · American University of the Middle East · Doc AUM-DBF-27-PR-001 · Rev A · 9 Oct 2026
Generated by procurement/make_pr.py from procurement/pr01_items.csv. Edit the CSV, then run procurement/build.sh; this workbook and the PDF are rebuilt together.
USD → KWD | 0.31083 | KWD per USD. currencyconvert.online, updated 2026-10-08 21:00 UTC (market rates). Replace with the CBK rate if purchasing requires it; every KWD cell follows this one.
GBP → USD | 1.3229 | USD per GBP. currencyconvert.online, updated 2026-10-08 21:00 UTC (market rates).
How to read the Items sheet
Status, Buy now: the specification is fixed; order now.
Status, Budget hold: the category and quantity are known, but the exact part follows the 13 Oct sizing gate (analysis Scripts 3–5). Reserve the budget now; part numbers follow on 14 Oct.
Price basis, Listing: the vendor's listed price, checked on 9 Oct 2026 (URL in column P). Column R says whether it was read on the vendor page or taken from search results for that page, which can lag the live page. A reference, not a quote.
Price basis, Estimate: a planning figure that has not been verified. Get a quote.
Prices exclude shipping, duties and VAT unless the vendor column says otherwise.
Purchasing constraints from the contest rules (2026–27 draft)
Receivers: ExpressLRS 2.4 GHz with PWM outputs (team decision, 8 Oct 2026). Do not substitute CRSF-only receivers: they need a flight controller, and flight controllers are banned (§3.2.1, §4.2.1). Buy FCC firmware versions: the radio must use a legal US frequency (§3.2.1).
Batteries: every pack (propulsion, receiver, sensor) must be commercial off-the-shelf, unaltered, with the manufacturer's label stating chemistry, capacity, voltage and C-rating (§3.2.3, §3.1.1). Propulsion packs ≤ 100 Wh each and ≤ 100 Wh in total (§3.2.3.2). Keep the original packaging: tech inspection checks it (§4.2.3).
Charging sacks: commercial, unaltered, manufacturer-labelled (§3.2.3).
Fuses: blade type in a separate harness; rating ≤ the pack's maximum continuous current, capped at 100 A (§3.2.3.1, §3.2.3.2).
Arming plug: wire the same gauge as the pack leads or heavier (§3.2.2).
ESCs: the BEC must be disabled, and a separate receiver battery is mandatory (§3.2.3, FAQ A.3).
No cameras, GPS, autopilots or flight controllers anywhere on the airplane (§3.2.1, §4.2.1).
Hatches: positive mechanical latches; magnets are not acceptable (§4.2.1).
Not in this request (budget items tracked separately)
Fly-off registration fee: US$550 per team (§2.6).
AIAA student membership: US$37 per member per year (aiaa.org dues page, checked 9 Oct 2026); required for every team member (§1.1, §2.1).
AMA membership for the pilot (§1.2): price to be confirmed with AMA.
Travel to Tucson and aircraft freight: separate travel request. Contingency: set by the team lead.